## Template for institutions
HREiR Action plan template (Jan 2023-Jan 2026)
Details
| Institution name: | Sheffield Hallam University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 7 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2023-01-01 |  |  |  | Research staff |  | 193 | 72 Research Assistants, 56 Research Fellows, 43 Senior Research Fellows, 21 Principal Research Fellows and 1 senior manager
| Institutional context: | The University employs around 1687 academic staff (excluding Associate Lecturers who do not have research as part of their employment contract). Our Academic Careers Framework sets out expectations for progression across four strands; i) academic citizenship and leadership; ii) research and innovation; iii) teaching and learning; iv) external and professional engagement. Staff can move flexibly across these strands, however, our target audience for the Concordat are those that follow the research and innovation strand. Our Early Career Researchers include our Research Assistants and Research Fellows (128 headcount); however, to support inclusivity in line with our Hallam Values, we support a wider, self-identification of Early Career Research status recognising the range of career paths at our institution including those from professional practice and industry. |  |  |  | Postgraduate researchers |  | 681 | Secondary audience for Concordat
[6 empty] | Research and teaching staff |  | 435 | Academics that are designated as having ‘Significant Responsibility for Research’ in line with REF 2021 Code of Practice
Teaching-only staff
Technicians
Clinicians
Professional support staff
[6 empty] | Other (please provide numbers and details): |  |  | Our secondary audience includes our remaining academic population who may be working towards gaining Significant Responsibility for Research and our postgraduate research students.
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Sheffield Hallam context: CEDARS 2021 - awareness of the Researcher Development Concordat and Research Integrity Concordat is higher amongst respondents compared to the sector. 67% of respondents are aware of/understand the Researcher Development Concordat and 66% are aware of/understand the Research Integrity Concordat. This is an increase from the 2019 surveys - CROS 2019: 36% awareness of the Concordat and 29% awareness of the HR Excellence in Research award. Our future focus is on engaging more staff with the feedback mechanisms and the activities that support delivery of the Concordat's obligations.
ECI1 | Ensure all relevant staff are aware of the Concordat. | Continue activities to raise awareness of the Concordat and mechanisms for staff feedback via RCOG, CEDARS, internal staff email bulletins as well as University, College and Research Institute committees. | N/A | Ongoing | RCOG chair | Ongoing improvement in awareness of the Concordat and HR Excellence in Research Award as measured by staff surveys (e.g. CEDARS). Baseline CEDARS 2021 (Q43): 67% have some understanding or awareness of the Researcher Development Concordat; 36% have some understanding or awareness of the HR Excellence in Research Award.
ECI1 | Ensure all relevant staff are aware of the Concordat. | Make sure the links to our Concordat pages are incorporated into guidance for new starters and existing research staff and their managers to clarify expectations (e.g. via the induction site, guidance to support Performance and Development Review, and the Academic Careers Framework). | Yes | 2023-08-01 | Researcher Training and Development Manager | Increased awareness measured via hit rates on the updated Researcher Development SharePoint pages to be launched in 2023.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Ensure an Equality Impact Assessment screening document is completed for all new research policies and initiatives. | N/A | Ongoing - review annually | PVC Research (RIC/RLG matters) Director Doctoral School (RDC matters) | Ongoing improvement in awareness of the Concordat and HR Excellence in Research Award as measured by staff surveys (e.g. CEDARS). Baseline CEDARS 2021 (Q43): 67% have some understanding or awareness of the Researcher Development Concordat; 36% have some understanding or awareness of the HR Excellence in Research Award.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | In the development of the new Researcher & Innovator development offer, we will actively consider systemic issues in research in the sector: specifically addressing how to overcome and reduce inequalities in relation to gender, race, disability, LGBT+, and harmful cultures and working practices. | N/A | 2024-12-01 | Head of Research and Innovation Development Academy (new appointment) | Equality data on research activity (e.g. grant submissions, internal funding allocations, significant responsibility for research) shows no inequalities in relation to protected characteristics. CEDARS Q41: The extent to which researchers agree that the institution is committed to equality and diversity. Baseline 2021 = 65%
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | As part of two OfS/Research England projects on race equity in PGR, we will review PGR admissions practices to support access to PGR study for underrepresented groups. | N/A | 2025-07-01 | Director Doctoral School | Equality data on access and participation in PGR study - project evaluation outcomes from the OfS/Research England funded projects.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Continue to seek feedback from staff via CEDARS and internal staff surveys (and from PGR students via PRES and Annual Feedback and Monitoring Exercise). Report CEDARS results to RLG and include key findings in the annual report to Board of Governors. | Yes | Ongoing with annual reporting | Chair RCOG (staff reporting and BoG) Director Doctoral School (PGR reporting) | Responses for the CEDARS Environment and Culture section Q37-40 (target = responses in line with the sector as a minimum). Baseline 2021: 52% would feel comfortable reporting an incident of discrimination and 50% trust that it would be investigated fairly. 53% would feel comfortable reporting an incident of bullying or harassment and 45% trust that it would be investigated fairly. 73% would feel comfortable reporting an incident of research misconduct and 66% trust that it would be investigated fairly. Increase in number of staff responding to CEDARS (baseline 2021 = 136 responses) | Outline annual reporting: Report to RLG - November/December Report to RIC - March Report to BoG - May RDC Annual Review - December
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Continue RCOG as a route for feedback and consultation on progress against the Concordat principles | N/A | Ongoing | Chair RCOG | ECR and College reps on RCOG are able to contribute to policy development and decision making. | 3 meetings per year
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Report on recommendations and outcomes from research environment and culture sessions held following the REF results in 2022. | Yes | Spring 2023 | Research Development Manager (Policy, Impact and Performance) | Availability of the report and progress made on recommendations.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Leadership groups to champion and bring to life the "Hallam Values" with their teams. | Yes | 2024-12-01 | Dean of Research and Head of Research and Innovation Development Academy (new appointment) | Hallam Values are embedded into Research & Innovation priorities and objectives, and reflected in relevant policies, processes and staff development.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Conduct and evaluate pilot of the use of narrative CV approaches and promote the value of contributions to the development of others and the wider R&I community. | N/A | 2023-12-01 | Dean of Research | CEDARS measure of feeling valued for contributions to developing researchers and supervising research students. Baseline 2021 = 69% and 79% respectively. Evaluation of narrative CV pilot.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Promote opportunities for staff to be involved in the three OfS/Research England projects on race equity in PGR. | N/A | Ongoing to Dec 2025 | OfS/RE Project leads | Evaluation outcomes from the OfS/Research England funded projects.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Promote and support the cross-University ECR Network. | N/A | Ongoing with annual reporting to May RCOG meetings | Researcher Training and Development Manager | A minimum of 4 ECR network events to run per year and active core group membership of at least 10.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working. Sheffield Hallam Context: CEDARS 2021 (136 respondents) - Managers are confident in responding to health and wellbeing issues (Q.25, 83%) and staff say that their managers promote a good work-life balance (74%) particularly for ECRs. Individuals actively maintain their mental health and wellbeing (Q.42, 76%) but are less positive about the role of the institution (Q.41, 59%) and working environment (Q.41, 38%) in supporting this, especially for ECRs.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Redesign the University's Wellbeing Strategy including a core element focused on wellbeing and workloads. | N/A | 2023-07-01 | HROD (Senior HRBP Lead for Wellbeing and Head of OP&C) | Internal staff survey measures of wellbeing. Target: positive scores >6.9 for Academic staff for: I am regularly able to cope with my workload.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Formulate and implement a University Wellbeing action plan to deliver the strategy. | N/A | 2024-07-01 | HROD (Senior HRBP Lead for Wellbeing and Head of OP&C) | Internal staff survey measures of wellbeing. Target: positive scores >6.9 for Academic staff for: I am regularly able to cope with my workload.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | Introduction of mental health training for managers as part of our commitment to the Universities Mental Health Charter (signed Autumn 2022). | N/A | 2024-07-01 | HROD (Senior HRBP Lead for Wellbeing and Head of OP&C) | Completion rates for mental health training. Internal staff survey measures of wellbeing. Target: positive scores >6.9 for Academic staff for: I feel comfortable raising any concerns I might have regarding my wellbeing with my line managers.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | Continue to run CEDARS and internal staff surveys to capture researchers' perceptions of research culture, wellbeing and mental health at work. Review results and produce recommendations for follow up. | N/A | Ongoing | Chair RCOG (CEDARS) Director HROD (internal staff surveys) | Internal staff survey measures of wellbeing. Target: positive scores >6.9 for Academic staff for: I am able to maintain a healthy work-life balance working here I feel mentally well at the moment. Staff engagement with e.g. focus group discussions leading to greater understanding of issues. CEDARS Q14: To what extent do you agree that your institution treats you fairly in relation to contracted workload. Baseline 2021 = 39% CEDARS Q41: To what extent do you agree that: Your institution actively promotes the importance of good mental health and wellbeing of staff. Baseline 2021 = 59% Your working environment supports your mental health and wellbeing. Baseline 2021 = 38% CEDARS Q25: managers' confidence in their ability to respond to any issues relating to health and wellbeing. Baseline 2021 = 82%
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q14: To what extent do you agree your institution treats you fairly in relation to: Requests for flexible working. Baseline 2021 = 71% Maternity, paternity, adoption and parental leave. Baseline 2021 = 51% CEDARS Q25: managers' confidence in their ability to manage requests for flexible working appropriately. Baseline 2021 = 68%
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q42 To what extent do you agree that you take positive action to maintain your mental health and wellbeing? Baseline 2021 = 77%
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents. Sheffield Hallam context: CEDARS 2021 (136 respondents) - 24% of Hallam respondents said they have felt personally discriminated against whilst at work (compared to the sector average of 19%) but only 8% have reported any incidents of discrimination to them or somebody else. A similar percentage (23%) of Hallam respondents said they have felt bullied or harassed, and 16% have reported an incident. Comfort at reporting incidents of bullying/harassment and discrimination is 53% and 52% respectively. In October 2021 we launched phase 1 of the Protect and Respect staff learning and development programme; staff are asked to attend an online workshop ‘Actively Building a Safe and Inclusive Culture’ and complete two E-learning modules ‘Being an Active Bystander’ and ‘Responding to Disclosures'.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Further enhance the existing programme of training and development that underpins our approach to tackle harassment, sexual misconduct and hate crime. Protect & Respect phase 2 will incorporate additional modules which explore the subject matter in more detail. | N/A | 2023-12-01 | HROD (HROD Manager - Cultural Development & Wellbeing) | Staff participation in Protect & Respect training. For 2021/22, 1031 staff have attended the online workshop, 642 staff have completed the Active Bystander module and 540 staff have completed the Responding to Disclosures module. CEDARS Q38. Q38 Baseline 2021: 45% of respondents trust that the institution would investigate any reported incidents of bullying and harassment fairly (sector = 60%). Q38 Baseline 2021: 61% of respondents are familiar with the mechanisms to report bullying or harassment; 53% would feel comfortable reporting an incident.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Implement the new guidance and process on "Compliance with Funder Bullying and Harassment Policies" developed by HROD and RIS in October 2022 for all relevant funders | N/A | 2023-01-01 | RIS (Head of Research Services) | Evaluation of process and number of compliance breaches.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | Continue to encourage the reporting of incidents via the University's "Report and Support" process - promote the use of this mechanism in staff areas (in addition to existing student areas). | Yes | 2024-07-01 | HROD (Senior HRBP Lead for Harassment, Sexual Misconduct and Hate Crime Programme) | CEDARS Q25: managers' confidence in their ability to respond to any issues relating to bullying and harassment. Baseline 2021: 63% of managers are confident/fully confident in responding to issues relating to bullying and harassment (sector = 62%)
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q37 and 38. Q37 Baseline 2021: 59% of respondents are familiar with process for reporting incidents of discrimination; 52% would feel comfortable reporting an incident. Q38 Baseline 2021: 61% of respondents are familiar with the mechanisms to report bullying or harassment; 53% would feel comfortable reporting an incident.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in, aware of and adopt practices enhancing equality, diversity and inclusion. Sheffield Hallam context: Our Equality Objectives 2021-24 embody the university’s ambition to create a transformational and aspirational culture of inclusion for all students and staff. Our future actions will be driven by the Equality Objectives and will focus on developing the rights skills, culture and environment to enable EDI to be embedded in all we do"
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Continue to promote and further enhance the existing programme of training and development that underpins our approach to tackle harassment, sexual misconduct and hate crime "Protect & Respect". Implement Phase 2 of this programme to incorporate additional modules which explore the subject matter in more detail. Make this training mandatory for our Senior Leadership Group (all academic and professional services leaders) and recommended for all other managers. | N/A | 2023-12-01 | HROD (HROD Manager - Cultural Development & Wellbeing) | Internal staff survey measures of wellbeing. Target: positive scores >6.9 for: I feel comfortable being myself when I'm at work. CEDARS Q26 Number of managers who report having undertaken training and other CPD in EDI and mental health and wellbeing. Baseline 2021 = 61% for EDI and 39% for mental health and wellbeing.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Embed the requirement for all staff to have an objective related to EDI in the annual Performance and Development Review process. | N/A | 2023-07-01 | HROD (Head of OP&C) | CEDARS Q41: The extent to which researchers agree that the institution is committed to equality and diversity. Baseline 2021 = 65%
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Translate the Hallam Values into a common set of behaviours expected of all employees. | N/A | 2023-07-01 | CPO (People Portfolio Operations Manager) | Hallam Values are embedded into Research & Innovation priorities and objectives, and reflected in relevant policies, processes and staff development.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Research Leadership Group to embed EDI into the forward research and innovation strategy and associated workstreams. | N/A | 2023-07-01 | RLG (PVC R&I) | CEDARS Q41: The extent to which researchers agree that the institution is committed to equality and diversity. Baseline 2021 = 65%
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Explore closer links, shared objectives and opportunities for cross-cutting activity with the University’s work under the Race Equality Charter, particularly around data sharing and input into new initiatives and mechanisms across the R&I portfolio. | N/A | 2023-12-23 | PVC R&I (as Race champion) | CEDARS Q37: Staff are treated fairly irrespective of any protected characteristics. Baseline 2021 = 50%
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q33 Number of researchers who report having undertaken training and other CPD in EDI and mental health and wellbeing. Baseline 2021 = 75% for EDI and 43% for mental health and wellbeing.
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct. Sheffield Hallam context: CEDARS 2021 (136 respondents): 76% of respondents believe the institution promotes the highest level of Research Integrity. The University is a signatory to the Research Integrity Concordat; 66% of CEDARS respondents were aware of the Concordat. Two expectations documents - responsibilities of Researchers and Responsibilities of Heads of Departments and Directors of Research Centres - are circulated to all research staff on an annual basis and available on our website via link 1. Training on research ethics and integrity is provided to new PGR students as part of their induction.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Actions to support this obligation are embedded within the University's Research Integrity Concordat commitment - see link 1 under supplementary information below. | N/A | N/A | Head of University Research Ethics | The number of research misconduct cases is reported in our University Research Ethics Committee annual report https://www.shu.ac.uk/research/excellence/ethics-and-integrity/contacts-and-committees.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Expand the pool of active research ethics reviewers to increase awareness and understanding of good research ethics practice and the internal and external requirements. | N/A | 2024-12-01 | Head of University Research Ethics | Expand to ethics reviewer pool from 250 to at least 500 researchers. ECRs and 2nd year doctoral researchers onwards to be encouraged to be reviewers as development activity gained through supported experiential learning and annual training (target 50 ECRs)
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Embed online research integrity course for new starters and as a recommended CPD activity for researchers. | Yes | 2023-09-01 | RIS (PIP team and Head of University Research Ethics) | Number of researchers completing the Research Integrity online training course. Baseline = 87 CEDARS Q26 & 33 Baseline 2021: 67% of managers and 49% of researchers report having undertaken training in research integrity.
ECM3 | Ensure managers report and address incidents of poor research integrity. | Actions to support this obligation are embedded within the University's Research Integrity Concordat commitment - see link 1 under supplementary information below. | N/A | N/A | Head of University Research Ethics | CEDARS Q39 Baseline 2021: 66% of respondents trust that reported incidents of research misconduct would be investigated fairly; 65% trust that the institution would take action if appropriate.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | Actions to support this obligation are embedded within the University's Research Integrity Concordat commitment - see link 1 under supplementary information below. | N/A | N/A | Head of University Research Ethics | CEDARS Q43 Baseline 2021: 37% of respondents have 'some understanding' of the Concordat to Support Research Integrity. CEDARS Q40 Baseline 2021: 9% of respondents have personally felt pressured into compromising their research standards or integrity.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q39 Baseline 2021: 64% of respondents are familiar with the institution's mechanisms to report incidents of research misconduct; 73% would feel comfortable reporting any incidents.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | We will provide opportunities for researchers and managers to co-create the new R&I Development Offer. | N/A | 2024-12-01 | Head of Research and Innovation Development Academy (new appointment) | CEDARS Q 14. To what extent do your agree that your institution treats you fairly in relation to: Opportunities to participate in decision-making processes. Baseline 2021 = 53%
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | We will continue to seek the input and views of ECRs and managers via RCOG. | N/A | Ongoing | Chair RCOG | ECR and College reps on RCOG are able to contribute to policy development and decision making.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | We will provide opportunities for managers to co-create the new Sheffield Hallam Research and Innovation Funding Programme (SHRIF). | N/A | SHRIF launched Feb 23. | PVC Research and Innovation and Dean of Research | CEDARS Q16. To what extent does your institution value the contributions that you make to: Institutional policy and decision-making? Baseline 2021 = 46% ('to some extent' or higher)
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | N/A
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | We will provide opportunities for researchers to co-create the new Sheffield Hallam Research and Innovation Funding Programme (SHRIF). | N/A | SHRIF launched Feb 23. | PVC Research and Innovation and Dean of Research | CEDARS Q16: Percentage of researchers who report having engaged in: Participation in policy & decision-making. Baseline 2021 = 12% have done this, 50% would like to do this.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Continue to facilitate ECR Network and encourage 2-way feedback with RLG to inform policy development. | N/A | Ongoing | Researcher Training and Development Manager | Input from ECR reps at RCOG and RI Leadership meetings / relevant working groups. CEDARS Q16. To what extent does your institution value the contributions that you make to: Institutional policy and decision-making? Baseline 2021 = 46% ('to some extent' or higher) CEDARS Q34:What is your level of interest in engaging in the following aspects of the research system?: Participation in institution policy and decision-making. Baseline 2021 = 12% have done this, 50% would like to do this.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | N/A
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation. Sheffield Hallam context: The University developed an Inclusive Recruitment Implementation Plan in February 2021, actions include the Equal Merit Principle - used where there is 20% or less representation of staff from racially minoritised communities within a college department or directorate. All Chairs of interview panels are required to complete an EDI training module. In CEDARS 2021 (136 respondents), of the 26 respondents who had been recruited within the last 2 years, the majority believe that this process was fair (88% agree/strongly agree), inclusive (81%), transparent (81%) and merit-based (85%) but fewer found their induction useful (69% at local level, 64% at department/unit level and 50% at institution level). Out of the 26 new starters, 4 were not offered an institutional induction and 5 were not offered a department or local induction. The focus therefore is on enhancing the induction for new staff researchers and ensuring that all new staff are able to access information to support them in their role. For new PGR supervisors, we offer a delivered supervisor development programme and an online course on supervising doctoral studies. For supervisors with some experience, we offer a range of development sessions delivered via the 'supervisor passport'. Research Institutes also provide ongoing supervisor CPD.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Conduct and evaluate pilot to understand the merit of introducing Narrative CVs for our internal funding schemes and its wider implications for recruitment. | N/A | SHRIF launched Feb 23, review May 23 | Dean of Research | CEDARS Q25: managers' confidence in their ability to use inclusive, equitable and transparent recruitment processes. Baseline 2021 = 83% CEDARS Q19: researchers' perceptions of the recruitment, selection and appointment process being: Fair. Baseline 2021 = 88% Inclusive. Baseline 2021 = 81% Transparent. Baseline 2021 = 81% Merit-based. Baseline 2021 = 85% Demographic data on staff profile, as reported in our EDI annual report. Evaluation of narrative CV pilot.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Actions to support this obligation are embedded within the University's Athena SWAN commitment - see link 2 under supplementary information below. | N/A | N/A | Dean of Research (as Athena SWAN SAT Chair) | Gender balance of G6 Researcher roles to be more in line with the current academic workforce to ensure a more evenly balanced future talent pipeline. Baseline 20/21 = 40% Female (current academic workforce 51% Female)
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Embed DORA principles into academic staff recruitment by referencing our commitment to the responsible use of metrics in guidance and training for recruiting managers and panels. | Yes | 2023-05-01 | HROD (Recruitment & Reward) | Guidance updated to include reference and links to DORA principles CEDARS Q25: managers' confidence in their ability to use inclusive, equitable and transparent recruitment processes. Baseline 2021 = 83% CEDARS Q19: researchers' perceptions of the recruitment, selection and appointment process being: Fair. Baseline 2021 = 88% Inclusive. Baseline 2021 = 81% Transparent. Baseline 2021 = 81% Merit-based. Baseline 2021 = 85%
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Ensure that online materials, courses etc. are easily accessible and curated to support induction for new staff. Review the institutional-level researcher induction to ensure an effective blended learning approach. | N/A | 2023-10-01 | Researcher Training and Development Manager | CEDARS Q20: researchers' perceptions of how useful their induction was: at institution level. Baseline 2021 = 50% (very useful/useful) at dept/faculty level. Baseline 2021 = 62% local to their current role. Baseline 2021 = 69%
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Development of the "academic induction journal" to include research-specific elements and CPD expectations with reference to our Concordat obligations. | Yes | 2023-07-01 | HROD (Head of OP&C) | Positive feedback from new starters on the usefulness of the induction journal as a guidance document and reflection tool.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Develop a research supervisor handbook (supplementing the delivered Supervisor Development Programme) to bring together and signpost relevant policies and practices relating to PGR supervision. | N/A | 2023-07-01 | Doctoral School Manager | Awareness of supervisor handbook, feedback from users via e.g. annual feedback monitoring survey and RDC.
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression. Sheffield Hallam context: We updated our Professor and Associate Professor Progression process in early 2020. The changes included embedding the Academic Careers Framework (ACF) within the Professor/Associate Professor (P/AP) progression process, moving from a biannual to an annual call for applications and aligning the processes for Professor and Associate Professor progression. This new process has enabled us to analyse outcomes by protected characteristics and identify where there is under-representation of certain groups at Professor and Associate Professor levels. On the basis of this data, we have taken steps to address the under-representation at P/AP levels of women and of Black, Asian and minority ethnic staff. We will continue to monitor the data to analyse the extent to which these measures are addressing the differential outcomes for, and under-representation of, certain groups. CEDARS (2021) revealed that only 33% of our researchers agree that there are equitable opportunities for career progression and our ECRs were less likely to believe that promotion and progression are fair.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | We will evaluate the new Early Career Research and Innovation Fellowship (ECRIF) scheme to understand its impact on the academic progression outcomes of participants. | N/A | 2025-07-01 | Dean of Research | Academic progression success rates of ECRIF participants. CEDARS Q17. To what extent do you agree that: The promotion pathways and processes at my institution are clear to me. Baseline 2021 = 50% My institution has equitable opportunities for career progression. baseline 2021 = 33%
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | We will provide delivered sessions and resources to support researchers, particularly ECRs and research fellows, to prepare narrative CVs in support of grant applications, as well as more generally reflecting on their skills and achievements. Also provide delivered sessions and resources to support panel members in reviewing researchers' narrative CVs. [Also an action under PCDR3]. | N/A | 2023-07-01 | Researcher Training and Development Manager | Sessions for researchers and reviewers developed and delivered, and supporting resources available. CEDARS Q14. Researchers' perceptions of fair treatment in relation to: Opportunities for promotion and progression. Baseline 2021 = 47%
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities. Shefield Hallam context: A regular managers' brief is circulated to all line managers by email, providing updates on policies and processes relevant to line managers. All participants in recruitment panels are required to complete EDI training, with an additional requirement for Chairs of panels. Research Institutes hold formal grant management and review meetings as part of post-award governance.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | Implement the new guidance and process on "Compliance with Funder Bullying and Harassment Policies" developed by HROD and RIS in October 2022 for all relevant funders [ECI3]. | N/A | 2023-01-01 | RIS (Head of Research Services) | CEDARS Q25. Managers' confidence in relation to: Giving guidance to researchers on redeployment processes. Baseline 2021= 28% confident/fully confident.
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | Completion figures for annual UKRI Researchfish reporting period
ER2 | Researchers understand their reporting obligations and responsibilities. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | N/A
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews. Sheffield Hallam context: A regular managers' brief is circulated to all line managers by email, providing updates on policies and processes relevant to line managers. All participants in recruitment panels are required to complete EDI training, with an additional requirement for Chairs of panels. An annual Performance and Development Review process is in place, with supporting guidance for academic staff reviewers and reviewees. Our 'Leadership and Management Essentials' programme consists of a series of facilitated workshops delivered online or in-person, providing practical information about leading and managing staff.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Promote the new Leadership and Management Essentials training programme aimed at G6 to G9 managers (and new managers at Senior Staff grade). Ensure flexibility for staff by allowing modular activity based on a needs-analysis as identified by managers. Expand the training to cover new topics including performance management. | N/A | 2023-12-01 | HROD (Head of OP&C) | CEDARS Q25. Managers' confidence in relation to: Provide effective feedback to individual researchers. Baseline 2021 = 95% Deal with poor performance of researchers. Baseline 2021 = 58%
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Align Academic Work Planning (AWP) to refreshed Research and Innovation objectives - undertake a major transition in the way that R&I time is allocated for research, building on our REF Code of Practice but with more clear and transparent time allocations for different research activity. Ensure fixed time for research leadership. | N/A | 2023-04-01 | AWP Leadership Group (and specifically Dean of Research as a member) | Effective allocation of staff time and associated significant responsibility for research (SRR), research leadership and innovation (knowledge exchange) at each annual cycle that can be subject to audit. Baseline of ~500 Headcount staff with SRR to be at least maintained.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Continue to consolidate and embed the Academic Careers Framework (ACF) providing transparent career progression criteria. | N/A | Ongoing | CPO (People Portfolio Operations Manager) | Number of staff securing progression via the research and innovation strand of the ACF. Baseline 2021/22 = Associate Professor 5; Professor 3.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q25. Managers' confidence in relation to: Manage appraisal/review processes effectively. Baseline 2021 = 81% CEDARS Q26: Percentage of managers who report having undertaken training and other CPD in: Conducting appraisals. Baseline 2021 = 35% Leading a research group. Baseline 2021 = 26% Managing staff performance. Baseline 2021 = 38% Supervising doctoral researchers. Baseline 2021 = 89% Leadership. Baseline 2021 = 42%
EM4 | Managers actively engage in regular constructive performance management with their researchers. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q28: Percentage of researchers who agree that their immediate manager: Clearly articulates their expectations of me with respect to my role and performance. Baseline 2021 = 69% Provides clear, constructive and timely feedback on my performance. Baseline 2021 = 57%
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | Percentage of academic staff who report having received an appraisal (via Core). Baseline 2022 = 32% research staff, 38% teaching, 29% senior staff (academic)
Job security
The aim of this obligation is to improve the job security of researchers. Sheffield Hallam context: Seventy of our staff on research contracts are fixed-term (36%). Where appropriate to the research centre's funding portfolio, use of permanent contracts allows staff to be deployed to different projects, leading to reduced casualisation and supporting career advancement.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | When developing internal funding schemes, consider the range of research centre funding/business models to ensure the scheme supports use of open-ended contracts where possible and does not unnecessarily or inadvertently incentivise employment of staff on fixed-term contracts. | N/A | Ongoing | Dean of Research (staff funding schemes) Director Doctoral School (PhD student scholarship schemes) | Internal funding schemes do not unnecessarily incentivise the employment of staff on fixed-term contracts. Number and percentage of staff on research contracts who are employed on a fixed-term basis (Baseline = 36%) and the reasons for employment on this basis.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it. Sheffield Hallam context: CEDARS 2021 - 72% of respondents agree that their manager encourages them to engage in personal and career development activities. However, only 15% of respondents report having engaged in 10 or more days' CPD. We implemented new functionality within the HR system to allow staff to record their CPD activity and enable us to report; take-up has been limited and only 23 academic staff have recorded their CPD in this way. We have conducted an audit of all activities and resources associated with researcher and innovator development at Sheffield Hallam, mapped against the Vitae RDF, and identified 600+ including programmes, sessions and online resources. Under new R&I leadership, we are developing plans for a Researcher and Innovator Development programme which will rationalise the opportunities and ensure the portfolio is balanced against the RDF. Aligned with our R&I strategy, we will launch a Researcher and Innovator Academy to bring together development across all career stages, support researchers to engage in CPD, and develop new provision which supports career transitions.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Recruit a leadership post to head up the Academy and develop a 3-5 year delivery plan | N/A | 2023-07-01 | Dean of Research | CEDARS Q30: the extent to which researchers agree that: You are aware of the support your institution provides for your career and professional development. Baseline 2021 = 40%
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | We will develop a new, co-created Researcher & Innovator development offer that will support staff to realise their full potential as researchers, innovators, collaborators and influencers. | N/A | 2024-12-01 | Head of Research and Innovation Development Academy (new appointment) | Number of staff (at different career stages) participating in the R&I development offer. Engagement with the two signature programmes - Early Career Research and Innovation Fellowship and Emerging Leaders.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | Continue to encourage researchers to record their CPD activities and review engagement with the online CPD recording tool. | Yes | 2023-10-01 | Chair RCOG | Core data on CPD recording. For 2021/22, 23 academic staff including 4 on research-only contracts had used the CPD recording functionality in Core. CEDARS Q35. Researchers' reports of number of days training and other CPD undertaken over the past 12 months. Baseline 2021 = 10 or more days = 15% 5 to 9 days = 15% 3 to 4 days = 24% 1 to 2 days = 21% less than 1 day = 26%
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q30: the extent to which researchers agree that: Your manager/supervisor encourages you to engage in personal and career development activities. Baseline 2021 = 72% You have time to develop your leadership skills. Baseline 2021 = 30% You have time to develop your research identity. Baseline 2021 = 34%
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q28. The extent to which researchers agree that their immediate line manager: supports me in my broader career aspirations. Baseline 2021 =63%
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews. Sheffield Hallam Context: An annual Performance and Development Review process is in place, with supporting guidance for academic staff reviewers and reviewees. The PDR process has been externally audited and, as a result, we are implementing an action plan to refresh the annual process.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | New guidance available on the intranet on how to conduct a quality Performance and Development Review (PDR) which includes links to the ACF. | N/A | 2023-12-01 | HROD (Head of OP&C) | CEDARS Q25. Confidence in actively supporting researchers in working towards their career aspirations. Baseline 2021 = 89%
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | For the 2022 annual PDR period, we implemented self-reporting of Performance and Development Review completion on our HR system. Going forward, we will continue to promote the recording of PDRs and monitor completion rates for academic/research staff. | N/A | October annually | HROD (Head of OP&C) | Percentage of Academic/research staff who report having completed a PDR. Baseline 2022 = 41.76% (excluding Associate Lecturers). CEDARS Q31. Percentage of researchers who have a formal career development review and the perceived usefulness (% who found it Very useful/useful). Baseline 2021 = 26% report having a formal review, of which 86% found it useful or very useful
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q25. Confidence in actively supporting researchers in working towards their career aspirations. Baseline 2021 = 89%
PCDR4 | Researchers positively engage in career development reviews with their managers. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q30: the extent to which researchers agree that: You have a clear career development plan. Baseline 2021 = 33%
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience. Sheffield Hallam context: The University is participating in a working group to look at wider uses for the Resume for Research and Innovation (narrative CVs). In February 2021 we launched our Research and Innovation Development Conversations; 153 researchers (including our ECRIFs) participated in an individual one-hour interview with members of RIS, providing researchers with opportunity to discuss their ambitions and associated challenges. Outcomes included a greater understanding of support needs to inform training and development provision and an understanding of research’ plans to enable focused support for grant bidding activity. New workshops have been delivered on fellowships, careers, generating impact, and grant writing. Data from CEDARS Q32 (n = 49) to understand career aspirations of research staff show that the majority (63%) of respondents aspire to an academic career; 19% aspire to a research career beyond academia; 7% aspire to 'other occupations' and 9% don't know.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Continue to deliver the Early Career Research and Innovation Scheme (ECRIF) to provide a cohort of researchers with leadership potential to have time to develop research plans and ambitions over a 12-month period, receive active mentoring to support these ambitions and have access to development opportunities to support career development. | N/A | Ongoing subject to annual review | Dean of Research | All researchers on cohort 2 of the ECRIF scheme to be provided with a research-active mentor to support individual research and career aspirations. Sustained programme of mentoring and development sessions for ECRIFs (min 4). Networking space for the ECRIFs to lead and self manage their engagement as a cohort (min 4)
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Undertake an end-of programme review for cohort 1 and 2 of the ECRIF scheme ensuring learning and experience is fed into any future programmes. | N/A | 2023-09-01 | Dean of Research | Target 80% response rate for end-of-programme review.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | New R&I development offer to review existing mentoring provision and identify any gaps for researchers. Continue to identify and share best practice. | Yes | 2024-07-01 | Researcher Training and Development Manager | CEDARS (institutional question) measure of awareness of mentoring opportunities. Baseline 51% in 2021.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Survey staff to understand staff needs and gaps in relation to advice on career management | Yes | 2023-07-01 | Researcher Training and Development Manager | Information gathered regarding the career advice requirements of our researchers via CEDARS institutional questions and follow on focus groups. CEDARS responses in relation to career and professional development Q.30 & Q.33 to understand the potential demand for CPD in career management.
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | Provide delivered sessions and resources to support researchers, particularly ECRs and research fellows, to prepare narrative CVs in support of grant applications, as well as more generally reflecting on their skills and achievements. | N/A | 2023-07-01 | Researcher Training and Development Manager | Number of staff accessing delivered sessions.
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | Provide delivered sessions and resources to support panel members in reviewing researchers' narrative CVs. | N/A | 2023-07-01 | Researcher Training and Development Manager | Engagement with sessions and resources; evaluation of reviewer experience of narrative CV pilots.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities. Sheffield Hallam Context: Our 'Leadership and Management Essentials' programme consists of a series of facilitated workshops delivered online or in-person, providing practical information about leading and managing staff. It is designed to provide existing and new line managers, in both professional services and academic areas of the University, with essential skills, tools and techniques for leading and managing a team. We are investing in a new leadership position (Head of Research and Innovation Development Academy) and launching a new 'Research and Innovation Development Academy' to bring together, co-ordinate and enhance the development offer for academic staff. The Researcher and Innovator Development Programme will reflect the Hallam Values and build on our existing provision to offer flexible, highly personalised opportunities for development to researchers and innovators at all career stages. Our Research Strategy includes the development of internal funding schemes and initiatives to support a range of activities aligned to the external research and innovation agenda, supporting the spectrum of research and innovation at all stages, and raising our profile at all levels - institutional, research areas and individuals.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | Develop new Sheffield Hallam Research and Innovation Funding (SHRIF) schemes to include mechanisms to support the development of ideas and people to build capacity, capability and connectivity; aligned to a new researcher and innovator development programme. | N/A | SHRIF launched Feb 23, review annually | Dean of Research Head of Research and Innovation Development Academy (new appointment) | Launch three SHRIF calls per annum with a target of 50% female researchers and 15% researchers from a racially minoritised background, representative of University profiles.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | The R&I development offer to consider development across all career transitions, from PGR/ECR to Professor, and professional/academic transitions. | N/A | 2024-12-01 | Head of Research and Innovation Development Academy (new appointment) | A staff development offer which considers and supports key career transitions
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q30: the extent to which researchers agree that: You have time to develop your leadership skills. Baseline 2021 = 30% You have time to develop your research identity. Baseline 2021 = 34%
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | Continue to promote the Senior Leadership Development Programme (inclusive of elements addressing personal effectiveness) for the most senior research leads. [see also actions under EI4] | N/A | 2023-12-01 | HROD (Head of OP&C) | CEDARS Q26: Percentage of managers who report having undertaken training and other CPD in: Conducting appraisals. Baseline 2021 = 35% Leading a research group. Baseline 2021 = 26% Managing staff performance. Baseline 2021 = 38% Supervising doctoral researchers. Baseline 2021 = 89% Leadership. Baseline 2021 = 42%
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | Develop and deliver a leadership programme to a wider group of senior staff including Senior Staff Grades 1 and 2. | N/A | 2025-07-01 | HROD (Head of OP&C) | Engagement with leadership programme.
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Promote new and existing development programmes and materials that researchers can access to develop their research identity and leadership skills. | N/A | 2024-07-01 | Researcher Training and Development Manager | Engagement with the online Advancing your Research Career programme and the new Emerging Leaders programme (to be launched April 2023).
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | Develop new internal research and innovation funding schemes to include mechanisms to support the movement and development of people; routes for external collaboration; and the development of mutually beneficial external partnerships. | N/A | Launch new scheme (SHRIF) Feb 2023 | Dean of Research | Launch three SHRIF calls per annum including a stream to support people - monitor the number of staff participating in schemes and evaluation of outcomes
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | Scope and consider a University-wide scheme to encourage external placement/internship opportunities for PGR students. | N/A | 2023-07-01 | Director Doctoral School | Options scoped and presented as a proposal for RDC and RLG consideration.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | The Transforming Lives Collaborative PhD Scholarship Scheme provides an opportunity for supervisors and PGR students to work with external organisations as collaborative partners. Review data on participation in TL scholarship schemes to assess equity of access across research areas and (if data available) staff groups. | N/A | Refreshed scheme launched Dec 2022; review Oct 2024 | Director Doctoral School | An understanding of participation across different research areas, ultimately ensuring schemes which support opportunities for staff across all research areas.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | N/A
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Continue to provide opportunities for researchers to engage the public, businesses and other stakeholders with their research. | Yes | Ongoing | Dean of Research and RIS (Head of Innovation Services) | Overview of participation in and outcomes of PE and KE activities and a greater understanding of development needs and opportunity gaps. CEDARS Q34: Percentage of researchers who report having engaged in: Commercialisation. Baseline 2021 = 8% Knowledge exchange. Baseline = 28% Public policy development. Baseline 2021 = 18% Public engagement. Baseline 2021 = 35% Citizen science/co-creation. Baseline 2021 = 12% Experience of other employment sectors. Baseline = 18% Secondment/placement. Baseline 2021 = 4%
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Sheffield Hallam's Research Integrity Concordat commitment https://www.shu.ac.uk/research/excellence/ethics-and-integrity/integrity-concordat |  |  |  | ACF | Academic Careers Framework
2 | Equality, diversity and Inclusion at Sheffield Hallam https://www.shu.ac.uk/about-us/our-values/equality-and-diversity |  |  |  | AWP | Academic Work Planning
3 | Sheffield Hallam Values https://www.shu.ac.uk/about-us/our-values |  |  |  | BoG | Board of Governors
4 | EDI reports https://www.shu.ac.uk/about-us/our-values/equality-and-diversity/reports |  |  |  | CEDARS | Culture, Employment and Development in Academic Research Survey
5 |  |  |  |  | CPD | Continuing Professional Development
6 |  |  |  |  | CPO | Chief People Officer
7 |  |  |  |  | CROS | Careers in Research Online Survey
8 |  |  |  |  | DORA | The Declaration on Research Assessment
9 |  |  |  |  | ECR | Early Career Researcher
10 |  |  |  |  | ECRIF | Early Career Research and Innovation Fellowship Scheme
11 |  |  |  |  | EDI | Equality, Diversity and Inclusion
12 |  |  |  |  | EIA | Equality Impact Assessment
13 |  |  |  |  | HR | Human Resources
14 |  |  |  |  | HRBP | Human Resources Business Partner
15 |  |  |  |  | HROD | Human Resources and Organisational Development
16 |  |  |  |  | KE | Knowledge Exchange
17 |  |  |  |  | LGBT+ | Lesbian, Gay, Bisexual, Trans and Others
18 |  |  |  |  | OP&C | Organisational Performance and Culture (HROD)
19 |  |  |  |  | OfS/RE | Office for Students / Research England
20 |  |  |  |  | P/AP | Professor/Associate Professor
[5 empty] | PDR | Performance Development Review
[5 empty] | PE | Public Engagement
[5 empty] | PIP | Policy, Impact & Performance Team (RIS)
[5 empty] | PGR | Postgraduate Research Student
[5 empty] | PRES | Postgraduate Research Experience Survey
[5 empty] | PVC R&I | Pro-Vice Chancellor for Research and Innovation
[5 empty] | R&I | Research and Innovation
[5 empty] | RCOG | Researcher Concordat Operations Group
[5 empty] | RDC | Research Degrees Committee
[5 empty] | RDF | Researcher Development Framework
[5 empty] | REF | Research Excellence Framework
[5 empty] | RIC | Research and Innovation Committee
[5 empty] | RIS | Research and Innovation Services
[5 empty] | RLG | Research Leadership Group
[5 empty] | SAT | Athena SWAN Self Assessment Team
[5 empty] | SHRIF | Sheffield Hallam Research and Innovation Funding Programme
[5 empty] | SRR | Significant Responsibility for Research
[5 empty] | TL | Transforming Lives
[5 empty] | UKRI | UK Research and Innovation

## Funders' obligations
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.
For brevity, the remaining obligations have been omitted from this 'Guidance' sheet.

## Tips
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.